## Read me
Program scoping workbook
What it's for
Size every asset, system and deliverable a program touches, so the timeline, resourcing, cost and risk rest
on evidence rather than guesses. The example program here is a website and customer portal migration.
How to complete it
1. Each function has its own tab with a few example rows and blank rows. Replace the examples and add
what's missing. Mark rows Not applicable rather than deleting them.
2. Split a row when its owner, effort, timing or risk differ from the rest.
3. Effort: enter active quantity, % needing change, setup hours, average hours per item and QA hours.
The tab works out items to update, internal hours and FTE days.
4. Cost: add a blended hourly rate and any external or vendor cost. Total cost combines both.
5. Risk and timing: flag customer action, approvals, lead time, risk and whether old and new can run together.
6. Log the decisions everyone is planning around on Decisions, and the critical-path items on Dependencies.
Reading it
The Summary rolls every function up, with headline numbers and a chart of internal hours.
Rows shade when they need attention: critical risk, customer action, or work due by cutover.
To add a function, copy a function tab, rename it and add a row to the Summary that points to it.
Cell styles
Blue text on white = edit me · navy text on light blue = formula, leave it
All names and numbers in this template are examples. Estimate conservatively and note your assumptions.
Example input cell | Example calculated cell

## Summary
Program scope summary
Scope, effort, cost and risk by function. It fills in from the function tabs.
Internal hours |  | FTE days |  | Total estimated cost |  | Customer action items
By function
Function | Scoped lines | Items to update | Internal hours | FTE days | External cost | Total estimated cost | High or critical risk | Customer action
Marketing
Product
Engineering
IT & Security
Legal & Privacy
Sales Enablement
Sales & RevOps
Customer Success
Professional Services
Customer Support
Pre-Sales
Partners
HR
Finance & Procurement
Executive & Strategy
Total
Chart title
Internal hours by function

## Decisions
Decisions and assumptions
Decisions that change scope, sequencing or risk. Keep them here so every function plans against the same assumptions.
Decision or assumption | Why it changes scope | Current assumption or options | Status | Decision owner | Target date | Impact if delayed | Notes
Platform and hosting choice | Sets the build effort, integrations and vendor contracts. | Shortlist of two platforms | In review |  |  | High
Cutover approach | Big-bang or phased changes the peak workload and the risk. | Phased by region | Open |  |  | High
URL structure | Drives redirects, search ranking and every link in other systems. | Keep current paths where possible | Open |  |  | Critical
Content freeze window | Sets how long authors stop publishing before cutover. | Two weeks | Open |  |  | Medium
Legacy content treatment | Decides what is moved, archived or retired. | Move the last three years | Open |  |  | Medium
Customer notification threshold | Which changes need advance notice, and how much. | 30 days for anything customers configure | Open |  |  | High

## Dependencies
Critical dependencies and risks
Items most likely to set the critical path, or that need customers or third parties to act.
Dependency or risk | Lead function | Supporting functions | Why it's critical | Customer action? | External approval? | Minimum lead time (days) | Old and new side by side? | Decision or mitigation | Owner | Status | Target date | Notes
DNS and certificates for new hosts | IT & Security | Engineering; Marketing | Nothing goes live without them. | No | No | 14 | Yes | Order certificates as soon as hosts are named. |  | Scoping
Customer allowlist updates | IT & Security | Customer Success; Engineering | Customers' firewalls may block the new hosts. | Yes | No | 45 | Yes | Publish host list 45 days ahead. |  | Scoping
Single sign-on changes | Engineering | IT & Security; Customer Success | Customers on SSO lose access if this is missed. | Yes | No | 30 | Yes |  |  | Scoping
Privacy notice update | Legal & Privacy | Marketing | Must be live before the new site collects data. | No | Yes | 21 | No |  |  | Scoping
Marketplace listing changes | Partners | Marketing; Product | Third-party review cycles are outside our control. | No | Yes | 30 | Unknown |  |  | Scoping
Payment portal move | Finance & Procurement | Engineering | Billing must not be interrupted. | Yes | Yes | 60 | Yes |  |  | Scoping

## Marketing
Marketing · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Website | Web pages | Corporate site pages moving to the new platform | Web manager | Current CMS | 12 | 12 | 25% |  | Content update | Medium | 24 | 0.5 | 16 |  |  | 85 |  | 5000 |  | No | No | No | No | Platform choice confirmed | 45 | Low | Medium | No | Update | 0–30 days | Scoping | Example row: replace with your own estimate.
Website | URL redirects | Map old URLs to new ones to keep traffic and search ranking | Web manager | Web host | 250 | 188 | 50% |  | Full rebuild | Medium | 16 | 0.5 | 16 |  |  | 95 |  | 12000 |  | No | No | No | No |  | 14 | Critical | Low | Yes | Update | 0–30 days | Validated
Website | Web forms | Contact, demo and download forms | Marketing operations | Marketing automation | 60 | 36 | 75% |  | Multiple changes | High | 24 | 4 | 2 |  |  | 85 |  | 5000 |  | Yes | Yes | Partial | Yes |  | 30 | Medium | Medium | Yes | Update | 0–30 days | Not started
Email | Email templates | Newsletter and nurture templates that link to the site | Marketing operations | Marketing automation | 4 | 2 | 50% |  | URL / link | High | 4 | 0.5 | 2 |  |  | 85 |  | 5000 |  | No | No | Partial | No |  | 30 | Medium | High | No | Update | 31–90 days | Scoping
Content | Resource library | Guides, reports and case studies with site links | Content lead | Current CMS | 40 | 24 | 100% |  | Full rebuild | Medium | 40 | 4 | 4 |  |  | 85 |  | 5000 |  | No | Yes | Yes | No |  | 30 | High | Medium | Partial | Redirect | 31–90 days | Scoping
Social | Social profile links | Profile and bio links across social channels | Social lead | Social platforms | 60 | 60 | 75% |  | URL / link | Medium | 40 | 4 | 16 |  |  |  |  | 30000 |  | Yes | No | Partial | Yes |  | 60 | Medium | Medium | Yes | Merge | 0–30 days | Scoping
Marketing total

## Product
Product · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
In-product | Help links | Links from the product UI to help articles | Product manager | Product codebase | 60 | 54 | 50% |  | Technical configuration | High | 16 | 1 | 8 |  |  | 85 |  |  |  | Yes | No | No | No | Platform choice confirmed | 5 | Low | High | Yes | Update | Before cutover | Validated | Example row: replace with your own estimate.
Documentation | Release notes | Published notes that reference portal pages | Product marketing | Docs site | 40 | 36 | 75% |  | Technical configuration | High | 4 | 0.25 | 16 |  |  | 95 |  |  |  | No | No | No | No |  | 10 | Medium | Low | Partial | Update | 0–30 days | Validated
In-product | Notification emails | System emails sent from the product | Product manager | Notification service | 250 | 188 | 25% |  | Visual update | Low | 40 | 2 | 8 |  |  | 85 |  |  |  | No | Yes | No | No |  | 10 | Medium | Low | No | Update | Before cutover | Scoping
Documentation | Admin guides | Online and PDF admin guides | Technical writer | Docs site | 800 | 600 | 50% |  | Legal text | Low | 24 | 0.5 | 2 |  |  | 95 |  |  |  | No | No | Partial | Yes |  | 60 | Low | Medium | Partial | Retire | 0–30 days | Not started
Product total

## Engineering
Engineering · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Integrations | API documentation | Endpoint references and code samples | Engineering lead | Developer portal | 40 | 30 | 100% |  | Multiple changes | Low | 8 | 2 | 8 |  |  | 95 |  |  |  | No | No | No | No | Platform choice confirmed | 45 | Medium | Medium | Yes | Redirect | Before cutover | Validated | Example row: replace with your own estimate.
Integrations | Webhook endpoints | Callback URLs that customers configure | Engineering lead | Platform | 25 | 22 | 75% |  | Legal text | High | 16 | 0.5 | 4 |  |  | 85 |  |  |  | Yes | Yes | No | No |  | 60 | Critical | Critical | Partial | Update | Cutover day | Scoping
Authentication | Single sign-on settings | Identity provider setup for the portal | Platform engineer | Identity provider | 800 | 600 | 100% |  | URL / link | Critical | 8 | 1 | 4 |  |  | 95 |  | 12000 |  | No | Yes | Yes | No |  | 14 | High | High | No | Update | 0–30 days | Scoping
Infrastructure | Monitoring checks | Uptime and synthetic checks on portal pages | SRE lead | Monitoring tool | 250 | 188 | 100% |  | Full rebuild | High | 16 | 2 | 16 |  |  | 95 |  | 5000 |  | No | Yes | Yes | Yes |  | 5 | Low | High | No | Update | Cutover day | Validated
Engineering total

## IT & Security
IT & Security · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Network | DNS records | Records for the new portal and site hosts | IT lead | DNS provider | 800 | 480 | 25% |  | Technical configuration | Medium | 16 | 4 | 8 |  |  | 95 |  | 5000 |  | No | No | Yes | No | Platform choice confirmed | 45 | Critical | High | No | Merge | 31–90 days | Scoping | Example row: replace with your own estimate.
Security | TLS certificates | Certificates for the new hosts | Security engineer | Certificate manager | 4 | 3 | 100% |  | URL / link | Critical | 4 | 1 | 2 |  |  |  |  | 12000 |  | No | Yes | Yes | No |  | 5 | Critical | Critical | Yes | Update | Cutover day | Validated
Security | Allowlists | Firewall and proxy rules that name portal hosts | Security engineer | Firewall | 12 | 12 | 25% |  | URL / link | Critical | 4 | 2 | 2 |  |  |  |  | 12000 |  | No | No | Partial | No |  | 10 | High | Critical | Partial | Update | 31–90 days | Scoping
Workplace | Intranet links | Intranet pages and bookmarks that point to the portal | IT service desk | Intranet | 250 | 150 | 25% |  | Legal text | Critical | 24 | 4 | 4 |  |  |  |  | 12000 |  | Partial | No | Partial | No |  | 14 | Medium | Low | Partial | Update | Cutover day | Scoping
IT & Security total

## Legal & Privacy
Legal & Privacy · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Policies | Privacy notice | Notice covering the new platform and its processors | Privacy counsel | Website | 250 | 188 | 50% |  | Technical configuration | Low | 24 | 4 | 16 |  |  | 95 |  | 12000 |  | Partial | Yes | Yes | No | Platform choice confirmed | 45 | Critical | Medium | Partial | Update | Before cutover | Validated | Example row: replace with your own estimate.
Policies | Cookie consent | Consent tool set-up on the new site | Privacy counsel | Consent platform | 12 | 7 | 75% |  | Technical configuration | Medium | 16 | 0.5 | 8 |  |  | 85 |  |  |  | Partial | No | Yes | Yes |  | 14 | Medium | Low | No | Redirect | Before cutover | Validated
Contracts | Order form links | Order forms that point to online terms | Commercial counsel | Contract system | 250 | 225 | 75% |  | Legal text | Critical | 16 | 1 | 16 | [6 empty] | Partial | No | Partial | No |  | 14 | Low | High | Partial | Merge | Cutover day | Validated
Vendors | Data processing agreements | Agreement updates for the new hosting vendor | Privacy counsel | Contract system | 25 | 19 | 75% |  | URL / link | Medium | 8 | 4 | 8 |  |  | 85 |  |  |  | No | No | Yes | Yes |  | 10 | Critical | Medium | No | Update | Before cutover | Validated
Legal & Privacy total

## Sales Enablement
Sales Enablement · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Templates | Proposal templates | Proposals with portal screenshots and links | Enablement lead | Content hub | 12 | 7 | 50% |  | Multiple changes | High | 24 | 1 | 4 |  |  | 95 |  | 30000 |  | No | No | Partial | Yes | Platform choice confirmed | 14 | Low | Medium | No | Merge | Cutover day | Validated | Example row: replace with your own estimate.
Training | Sales training modules | Courses that demo the portal | Enablement lead | Learning platform | 60 | 54 | 75% |  | Multiple changes | Critical | 24 | 4 | 4 |  |  | 85 |  | 12000 |  | No | No | Yes | No |  | 10 | Critical | Critical | Partial | Merge | 31–90 days | Scoping
Collateral | Product one-pagers | Sell sheets with URLs and QR codes | Enablement lead | Content hub | 4 | 4 | 25% |  | Content update | Low | 4 | 0.5 | 4 |  |  | 95 |  | 30000 |  | No | Yes | Yes | No |  | 45 | Medium | Low | Yes | Redirect | Before cutover | Not started
Sales Enablement total

## Sales & RevOps
Sales & RevOps · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
CRM | Email sequences | Sales sequences with portal links | RevOps manager | CRM | 120 | 120 | 100% |  | URL / link | Medium | 16 | 1 | 8 |  |  | 95 |  | 5000 |  | Partial | Yes | No | Yes | Platform choice confirmed | 45 | Low | Medium | Partial | Update | 31–90 days | Scoping | Example row: replace with your own estimate.
CRM | Quote templates | Quotes with links to online terms | RevOps manager | Quoting tool | 40 | 36 | 50% |  | Visual update | Medium | 8 | 2 | 2 |  |  | 85 |  |  |  | No | No | No | No |  | 60 | Medium | Medium | Yes | Retire | 0–30 days | Not started
Reporting | Pipeline dashboards | Dashboards that track portal sign-ups | RevOps analyst | BI tool | 800 | 800 | 75% |  | Full rebuild | Critical | 16 | 2 | 16 |  |  |  |  | 30000 |  | No | No | Yes | No |  | 45 | High | Critical | Yes | Redirect | Before cutover | Not started
Sales & RevOps total

## Customer Success
Customer Success · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Onboarding | Onboarding guides | Welcome packs and getting-started guides | CS operations | Content hub | 12 | 7 | 50% |  | Full rebuild | Critical | 16 | 0.5 | 16 |  |  |  |  | 5000 |  | Partial | Yes | No | No | Platform choice confirmed | 60 | Medium | Critical | Partial | Merge | Before cutover | Scoping | Example row: replace with your own estimate.
Communications | Customer notices | Advance notice of the move and what changes | CS director | Email platform | 800 | 800 | 25% |  | Legal text | Medium | 40 | 0.5 | 16 | [6 empty] | No | No | No | Yes |  | 14 | Critical | Medium | No | Update | Before cutover | Scoping
Accounts | Success plans | Plans that reference portal features | CS manager | CS platform | 250 | 225 | 50% |  | Legal text | High | 8 | 4 | 4 | [6 empty] | Partial | No | No | No |  | 10 | Low | Critical | No | Retire | Before cutover | Validated
Customer Success total

## Professional Services
Professional Services · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Delivery | Implementation playbooks | Playbooks with portal set-up steps | PS lead | Content hub | 40 | 30 | 75% |  | Visual update | Critical | 4 | 4 | 2 | [6 empty] | No | Yes | Partial | Yes | Platform choice confirmed | 30 | Medium | Critical | Partial | Redirect | 31–90 days | Scoping | Example row: replace with your own estimate.
Delivery | Statement of work templates | SOW templates with URLs | PS operations | Contract system | 60 | 60 | 75% |  | Technical configuration | High | 16 | 4 | 4 | [6 empty] | Partial | No | No | No |  | 45 | Critical | High | Yes | Update | Before cutover | Validated
Training | Customer training courses | Instructor-led and on-demand courses | Training lead | Learning platform | 60 | 36 | 25% |  | Technical configuration | Medium | 16 | 4 | 8 |  |  |  |  | 30000 |  | No | No | Partial | No |  | 45 | Critical | Medium | Partial | Update | Cutover day | Scoping
Professional Services total

## Customer Support
Customer Support · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Knowledge base | Help articles | Articles with screenshots and portal links | Support content lead | Help center | 4 | 4 | 50% |  | URL / link | Medium | 24 | 1 | 8 | [6 empty] | Yes | No | Yes | No | Platform choice confirmed | 45 | Medium | Low | Partial | Update | Cutover day | Scoping | Example row: replace with your own estimate.
Tooling | Macros and saved replies | Saved replies that include URLs | Support operations | Ticketing system | 800 | 600 | 25% |  | Content update | Critical | 8 | 4 | 4 |  |  | 95 |  |  |  | Partial | No | Yes | No |  | 10 | Medium | Medium | Partial | Redirect | 31–90 days | Scoping
Tooling | Support portal | Ticket submission pages | Support operations | Ticketing system | 4 | 4 | 75% |  | Legal text | High | 8 | 4 | 16 |  |  | 95 |  | 12000 |  | No | No | Partial | No |  | 30 | Medium | Low | No | Merge | 0–30 days | Validated
Communications | Status page | Status page components and subscriber notices | Support operations | Status page tool | 12 | 7 | 75% |  | URL / link | Medium | 40 | 1 | 8 |  |  | 85 |  | 5000 |  | Yes | No | No | No |  | 60 | Critical | Low | Yes | Update | 31–90 days | Scoping
Customer Support total

## Pre-Sales
Pre-Sales · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Demo | Demo environments | Demo tenants on the current portal | Solutions lead | Demo platform | 25 | 25 | 50% |  | Content update | Critical | 8 | 0.25 | 16 |  |  | 95 |  |  |  | No | No | Partial | Yes | Platform choice confirmed | 60 | High | High | No | Redirect | 0–30 days | Not started | Example row: replace with your own estimate.
Templates | RFP answer library | Standard answers that mention hosting and URLs | Bid manager | RFP tool | 60 | 36 | 75% |  | Legal text | Critical | 40 | 0.5 | 2 |  |  | 85 |  | 30000 |  | No | No | No | No |  | 14 | High | Medium | No | Merge | 31–90 days | Not started
Demo | Recorded demos | Demo videos that show the portal | Solutions consultant | Video platform | 12 | 7 | 50% |  | URL / link | Critical | 4 | 1 | 16 | [6 empty] | No | No | Partial | No |  | 14 | Medium | Medium | Partial | Retire | 31–90 days | Scoping
Pre-Sales total

## Partners
Partners · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Portal | Partner portal pages | Partner pages and deal registration | Partner manager | Partner portal | 250 | 188 | 100% |  | Visual update | Medium | 8 | 1 | 2 |  |  | 85 |  |  |  | Partial | No | Partial | Yes | Platform choice confirmed | 5 | High | Medium | Partial | Update | Before cutover | Scoping | Example row: replace with your own estimate.
Enablement | Partner training | Partner courses and certifications | Partner enablement | Learning platform | 250 | 150 | 75% |  | URL / link | Medium | 4 | 4 | 4 |  |  |  |  | 12000 |  | No | Yes | No | No |  | 14 | High | Medium | No | Update | 31–90 days | Scoping
Marketplace | Marketplace listings | Third-party listings that link to the site | Partner manager | Marketplaces | 60 | 54 | 100% |  | Legal text | Medium | 4 | 0.5 | 8 |  |  | 85 |  |  |  | No | No | No | Yes |  | 60 | High | Medium | No | Redirect | Before cutover | Not started
Partners total

## HR
HR · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Recruiting | Careers pages | Job listings and the careers site | Talent lead | Applicant tracking | 800 | 720 | 75% |  | Full rebuild | Critical | 24 | 0.25 | 16 | [6 empty] | No | Yes | Yes | Yes | Platform choice confirmed | 45 | Medium | Critical | Yes | Redirect | Before cutover | Validated | Example row: replace with your own estimate.
Employees | Handbook links | Handbook pages that link to internal tools | HR operations | HR system | 120 | 108 | 50% |  | Legal text | High | 8 | 1 | 8 | [6 empty] | Partial | No | Partial | No |  | 60 | Medium | Medium | Partial | Redirect | Cutover day | Scoping
Recruiting | Offer letter templates | Templates with links to benefits pages | HR operations | HR system | 120 | 72 | 100% |  | Visual update | High | 4 | 0.5 | 2 |  |  |  |  | 12000 |  | Yes | No | Partial | No |  | 60 | High | Medium | Partial | Update | 0–30 days | Scoping
HR total

## Finance & Procurement
Finance & Procurement · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Billing | Invoice templates | Invoices with payment portal links | Billing lead | Billing system | 12 | 11 | 75% |  | URL / link | Medium | 24 | 2 | 2 |  |  | 95 |  | 12000 |  | No | Yes | Partial | Yes | Platform choice confirmed | 45 | High | High | Yes | Redirect | 0–30 days | Not started | Example row: replace with your own estimate.
Billing | Payment portal | Customer payment and account pages | Billing lead | Payment platform | 60 | 45 | 75% |  | Legal text | Critical | 4 | 0.25 | 4 |  |  | 85 |  | 5000 |  | No | No | No | Yes |  | 60 | Medium | Low | Yes | Update | 0–30 days | Scoping
Procurement | Vendor onboarding | Set-up and approvals for the new hosting vendor | Procurement lead | Procurement system | 4 | 4 | 25% |  | Full rebuild | Medium | 8 | 1 | 16 | [6 empty] | Partial | No | No | No |  | 60 | Critical | Low | Partial | Update | 31–90 days | Not started
Finance & Procurement total

## Executive & Strategy
Executive & Strategy · scope
Every asset, system and deliverable this function owns that the program touches. Blue text on white is yours to fill in. Light-blue cells calculate; leave them as they are.
Replace the example rows, add what's missing, and mark rows Not applicable instead of deleting them.
The item |  |  |  |  | Volume |  |  |  | Change |  | Effort |  |  |  |  | Cost |  |  |  | Readiness | [5 empty] | Risk |  |  | Plan
Asset category | Asset or deliverable | Description or example | Owner | System or location | Total quantity | Active quantity | % needing change | Items to update | Change type | Complexity | One-time setup hours | Avg hours per item | QA and review hours | Total internal hours | Internal FTE days | Blended hourly rate | Internal cost | External or vendor cost | Total estimated cost | Can bulk update or automate? | Customer action needed? | External notice needed? | External approval needed? | Dependency or prerequisite | Lead time (calendar days) | Business risk if missed | Customer disruption | Old and new run side by side? | Disposition | Required timing | Status | Notes and assumptions
Governance | Steering committee pack | Program updates and decisions | Chief of staff | Shared drive | 40 | 24 | 100% |  | Full rebuild | Medium | 16 | 0.5 | 8 |  |  | 95 |  | 30000 |  | No | No | No | No | Platform choice confirmed | 14 | Medium | Critical | Partial | Retire | Cutover day | Validated | Example row: replace with your own estimate.
Communications | Board update | Summary of timing, cost and risk | Chief of staff | Board portal | 250 | 225 | 75% |  | Technical configuration | Medium | 4 | 4 | 8 |  |  |  |  | 5000 |  | No | Yes | Partial | No |  | 60 | Critical | Critical | No | Update | Before cutover | Not started
Communications | All-hands announcement | Internal launch announcement | Internal comms lead | Intranet | 4 | 4 | 50% |  | Content update | Critical | 16 | 0.5 | 16 |  |  | 95 |  | 30000 |  | No | No | No | No |  | 14 | Medium | Medium | No | Retire | 31–90 days | Not started
Executive & Strategy total

## Lists
Lists and definitions
The choices behind the drop-downs, the FTE day setting and what each column means.
Drop-down lists
Change type | Level | Yes / no | Disposition | Required timing | Status | Decision status
Content update | Low | Yes | Update | Before cutover | Not started | Open
Visual update | Medium | No | Redirect | Cutover day | Scoping | In review
URL / link | High | Partial | Merge | 0–30 days | Validated | Decided
Legal text | Critical | Unknown | Keep as is | 31–90 days | Approved | Deferred
Technical configuration |  |  | Archive | 90+ days | In progress
Full rebuild |  |  | Retire | TBD | Complete
Multiple changes |  |  | No change |  | Not applicable
Review only
Setting
Hours per FTE day | 8
Column definitions
Column | What to enter
System or location | Where the item lives or is managed today: a CMS, CRM, shared drive, codebase or vendor platform.
Total quantity | Every known item of this kind, including old and archived ones.
Active quantity | Items still in use that need a look. Leave out anything already obsolete.
% needing change | Your best estimate of the share of active items that will need work.
Items to update | Calculated: active quantity × % needing change.
Change type | The main kind of change: content, visual, links, legal text, technical set-up, a rebuild, several, or review only.
Complexity | How hard the change is, counting effort, approvals, testing and risk: low, medium, high or critical.
One-time setup hours | Hours to build the new master, template or configuration once, before item-by-item work.
Avg hours per item | Hands-on hours to update one item once set-up is done.
QA and review hours | Total hours for review, testing, approvals and checks for the whole row, not per item.
Total internal hours | Calculated: setup hours + (items to update × avg hours per item) + QA hours.
Internal FTE days | Calculated: total internal hours ÷ hours per FTE day (set below). A planning measure, not a staffing plan.
Blended hourly rate | An agreed average hourly cost for the internal people doing the work.
Internal cost | Calculated: total internal hours × blended hourly rate.
External or vendor cost | Agencies, contractors, developers, printers, translators, software and other outside spend.
Total estimated cost | Calculated: internal cost + external or vendor cost.
Can bulk update or automate? | Whether scripts, bulk edits, global templates or configuration can do some of the work.
Customer action needed? | Whether customers must change something themselves, such as allowlists, integrations or SSO.
External notice needed? | Whether customers, partners, suppliers or others must be told, even if they don't act.
Lead time | Elapsed calendar days from start to done, including waiting and approvals. Different from effort.
Business risk if missed | The impact if the item isn't done right or on time: legal, financial, operational or reputational.
Customer disruption | How much customers would feel it if the change went wrong.
Old and new side by side? | Whether the current and new versions can run in parallel during the transition.
Disposition | What should happen to the item: update, redirect, merge, keep as is, archive, retire or no change.
Required timing | When it must be done relative to cutover: before, on the day, or within 30, 90 or more days.